SECTION 01 32 16

CONSTRUCTION PROGRESS SCHEDULE

Use this specification on projects of short duration (typically less than 6 months) and are technically simple and straightforward – Confer with MSD Project Manager

# PART 1 – GENERAL

## SECTION INCLUDES

### Scope.

### Software/Interface Requirements.

### Non-Compliance.

## RELATED SECTIONS

### General Conditions are included in Section 00 72 00, including Paragraph 6.04.

### Submittals are included in Section 01 33 00.

### Project Meetings are included in Section 01 31 19.

## SCOPE

### A clear and complete Schedule is required for the Project. Most importantly, the Schedule shall be a tool which the CONTRACTOR and his agents will use to manage their Work and scope of the Project. The schedule must provide a tool that all parties involved in the Project can use to understand the status of and intended Project plan throughout the execution of the Project.

### The CONTRACTOR shall manage the work following the sequence defined by the Schedule,  and it shall be the document from which Project progress is measured.

### The schedule shall reflect the activities of the CONTRACTOR and all subcontractors.

## SOFTWARE/INTERFACE REQUIREMENTS

### The CONTRACTOR shall use software which can be reduced to an electronic format to produce the Project schedule, including a summary Gantt Chart and any narrative or summary reports which identify critical activities in support of the Gantt Chart.

## NON-COMPLIANCE

### Pending an acceptable submission of the schedule, no partial payment will be made except in such amounts as may be approved by the CITY for materials received at the Project Site, plus any additional amounts that the CITY decides to release.

# PART 2 - PRODUCTS

## CONSTRUCTION PROGRESS SCHEDULES GENERAL CRITERIA

### The CONTRACTOR shall submit all Project Schedules to MSD.  In addition, the CONTRACTOR shall submit the schedule in PDF format and any “native files” of electronic software used to generate the Project Schedule and Gantt Chart PDF.

### The Project Schedule shall show the breakdown of Work into activities to the extent required to effectively manage the project.  The initial project schedule (baseline schedule) shall specify the progression of the Work from the Notice to Proceed (NTP) to the completion of the Work and shall be logically linked to include all milestones.

### The CONTRACTOR’s schedule shall be based upon lead times for all procurement related activities that lead to the delivery of permanent materials to the site.  Procurement activities include, but are not limited to, preparation of Submittals, review and acceptance of Submittals, materials fabrication, and materials delivery and shall comply with the requirements of the Contract Documents.

## CONSTRUCTION PROGRESS SCHEDULE BASELINE SUBMISSION

### The CONTRACTOR shall prepare and submit a Baseline Construction Progress Schedule for review at or prior to the Pre-Construction Meeting.

### The CONTRACTOR’s Baseline Schedule shall consist of the following as a minimum:

#### A Gantt chart plot, which must clearly and legibly show all activities and predecessors and shall display each activity’s identification number, description and duration.

#### The schedule packet, comprised of the Gantt chart and accompanying narrative shall clearly relate the sequence and interdependence of activities required for complete performance of the work, beginning with the expected Notice to Proceed (NTP) and concluding with the Contract Completion Date (CCD).

C.	When the CONTRACTOR’s Baseline  is reviewed and approved by the CITY, it becomes the “Approved Baseline” .  Any changes to the Baseline Schedule, other than status updates, require the approval of the CITY.

## CONSTRUCTION PROGRESS SCHEDULE UPDATE

### The CONTRACTOR shall provide an updated schedule packet as requested by the CITY.

### Updating the  schedule packet  shall consist of manually reflecting: actual start, physical percent complete, remaining duration, actual finish, and data date.  Updates shall also incorporate corrections or comments from the last submittal.

### In the event that an update indicates slippage in contract completion date (CCD) in excess of 10 working days, the CONTRACTOR will be required to submit a  Recovery Schedule reflecting changes in logic, duration, or sequencing required to recover lost time.  Upon approval by the CITY of the  Recovery Schedule, that  schedule becomes the new project Baseline Schedule.

## CONSTRUCTION PROGRESS SCHEDULE NARRATIVE

### The Schedule Narrative shall accompany the initial submittal of the CONTRACTOR’s schedule. The  Narrative shall support and augment the  Gantt Chart. It shall include, but is not limited to the following:

#### An explanation of the general sequence of the Work.

#### An explanation of the critical activities such as shop drawing activity, procurement purchase order releases and expected deliveries resulting there from, etc,

#### An explanation of physical constraints to completing the Work.

### A  Narrative shall accompany each update to the CONTRACTOR’s Schedule Packet and shall, at a minimum, address the following:

#### Milestones Completed.

#### Any actual or anticipated problems with delivery of materials or equipment.

#### Any corrective action undertaken by the CONTRACTOR to address schedule problems.

#### Anything impacting critical path, milestones, and contractual completion.

# 2.05	CONSTRUCTION PROGRESS SCHEDULE – TIME IMPACT ANALYSIS

If the contractor experiences a delay, through no fault of his own, he may request a time extension. The Contractor shall provide to the City, a notice of any delay, extending the duration of the overall project, within 5 working days of the event that has caused that delay. The contractor must submit to City, in accordance with the Document Control submittal process, a narrative giving sufficient detail as to the nature of the delay, why the contractor did not have control over the delay, and justification for the amount of additional time requested. MSD will review the request and, within 5 working days of receipt, will either accept; deny; or request additional information

# PART 3 – EXECUTION

## 3.01	CONSTRUCTION PROGRESS SCHEDULE SUBMISSION AND REPORTING REQUIREMENTS TABLE:

### The reports required by this section are to be prepared and submitted by the CONTRACTOR in accordance with Table 01 32 16-1 below.

Table 01 32 16-1: Table of Schedule Submittal Requirements

| No. | DESCRIPTION | SUBMITTED AT PRE-CON | SUBMITTED AS SPECIFIED |
| --- | --- | --- | --- |
| 1. | Baseline Construction Progress Schedule | v |  |
| 2. | Construction Progress Schedule Updates |  | v |
| 3. | Revised Construction Schedules/ Recovery Schedules |  | v |
| 4. | Time Impact Analysis |  | v |
| 5. | Schedule Narrative report | v | v |

.

END OF SECTION 01 32 16