SECTION 01 32 16

CONSTRUCTION PROGRESS SCHEDULE

[To be used for larger sewer and pump station  projects, typically 6 months or longer -  consult with MSD project manager which scheduling spec to use]

# PART 1 – GENERAL

## SECTION INCLUDES

### Scope.

### Software/Interface Requirements.

### Quality Assurance.

### Non-Compliance.

## RELATED SECTIONS

### General Conditions are included in Section 00 72 00, including Paragraph 6.04.

### Contract Considerations are included in Section 01 26 00, including Paragraph 1.03, Schedule of Values

### Submittals are included in Section 01 33 00.

### Project Meetings are included in Section 01 31 19.

### Substantial Completion as included in Section 01 77 19.

## SCOPE

### A clear and complete Construction Progress Schedule (CPS) is required for the Project. Most importantly, the CPS shall be a tool which the CONTRACTOR and his agents will use to manage their Work and scope of the Project. The schedule must provide a tool that all parties involved in the Project can use to understand the status of and intended Project plan throughout the execution of the Project.

### The CONTRACTOR shall manage the work following the sequence defined by the CPS, and the schedule shall be the document from which Project progress is measured.

### The schedule shall reflect the activities of the CONTRACTOR and all subcontractors.

## SOFTWARE/INTERFACE REQUIREMENTS

### The CONTRACTOR shall use modern Critical Path Methodology (CPM) scheduling software to produce the Project schedules, including the CPSs and reports as specified. This software shall run on the Microsoft Windows operating system and be able to produce electronic schedule files that are compatible with Primavera Project Manager Version P6 software.

## QUALITY ASSURANCE

### The CONTRACTOR shall employ a firm or individual to perform the work covered by this section that shall have substantive experience in using computer based scheduling programs on construction projects (the “Scheduling Consultant”).  The CONTRACTOR shall submit the following as a minimum:

#### Identification, qualifications, and experience of the members of the CONTRACTOR’s scheduling staff or any consultant’s staff.  The designated Scheduling Consultant shall have at least five (5) years of experience in the computerized scheduling of public or industrial construction work.  The CONTRACOR shall provide a resume for the designated individual(s) that details all qualifications, experience, and references for the CITY’s approval.

#### The CITY may reject any member of the CONTRACTOR’s scheduling staff or any of Contractor's Scheduling Consultant’s staff.  The CONTRACTOR shall promptly replace rejected personnel and resubmit the above required qualifications for acceptable personnel at no additional cost to the CITY.

## NON-COMPLIANCE

### Pending an acceptable submission of the CPS, no partial payment will be made except in such amounts as may be approved by the CITY for materials received at the Project Site, plus any additional amounts that the CITY decides to release.

# PART 2 - PRODUCTS

## CONSTRUCTION PROGRESS SCHEDULES GENERAL CRITERIA

### The CONTRACTOR shall submit all Project Schedules on 11” x 17” format.  In addition, the CONTRACTOR shall submit schedule in PDF format and the designated Primavera-compatible file format.  The initial submittal shall be made at or before the pre-construction meeting.

### The Project Schedules shall show the breakdown of Work into activities to the extent required to effectively manage the project.  The CPS shall specify the progression of the Work from the Notice to Proceed (NTP) to the completion of the Work and shall be logically linked to include all milestones.

### The CONTRACTOR’s CPS shall include all procurement related activities that lead to the delivery of permanent materials to the site.  Procurement activities include, but are not limited to, preparation of Submittals, review and acceptance of Submittals, materials fabrication, and materials delivery and shall comply with the requirements of the Contract Documents.

## CONSTRUCTION PROGRESS SCHEDULE BASELINE SUBMISSION

### The CONTRACTOR shall prepare and submit a Baseline Construction Progress Schedule for review at or prior to the Pre-Construction Meeting.

### The CONTRACTOR’s Baseline CPS shall consist of the following as a minimum:

#### A Gantt chart plot sorted by early start and early finish.  The plot must clearly and legibly show all activities and predecessors and shall display each activity’s identification number, description, original duration, remaining duration and total float value.  The plot shall clearly show the critical path.

#### The CPS must clearly show the sequence and interdependence of activities required for complete performance of the work, beginning with the Contract Start Date (CSD) and concluding with the Contract Completion Date (CCD). The maximum duration of any physical work activity shall not exceed twenty (20) working days (or one reporting cycle) unless approved by the CITY.

#### Tabular activity reports will be required as directed by the CITY and/or the CITY’s representative.

B.	When the CONTRACTOR’s Baseline CPS is reviewed and approved by the CITY, it becomes the “Approved Baseline” CPS.  Any changes to the Baseline CPS, other than status updates, require the approval of the CITY.

## CONSTRUCTION PROGRESS SCHEDULE UPDATE

### The Contractor shall provide an updated CPS on a monthly basis.

### Updating the CPS shall consist of manually reflecting: actual start, physical percent complete, remaining duration, actual finish, and data date.  Updates shall also incorporate corrections or comments from the last submittal.

### In the event that an update indicates negative float in excess of twenty (20) working days, the CONTRACTOR will be required to submit a CPS Recovery Schedule reflecting changes in logic, duration, or sequencing required to recover lost time.  Upon approval by the CITY of the CPS Recovery Schedule, that CPS becomes the new project Baseline CPS.

## CONSTRUCTION PROGRESS SCHEDULE NARRATIVE

### CPS Narrative shall accompany the initial submittal of the CONTRACTOR’s CPS. The CPS Narrative shall support and augment the CPM CPS. It shall include, but is not limited to the following:

#### An explanation of the general sequence of the Work.

#### An explanation of the Project critical path.

#### An explanation of physical constraints to completing the Work.

### A CPS Narrative shall accompany each update to the CONTRACTOR’s CPS and shall, at a minimum, address the following:

#### Milestones Completed.

#### Any actual or anticipated problems with delivery of materials or equipment.

#### Any corrective action undertaken by the CONTRACTOR to address CPS problems.

#### Anything impacting critical path, milestones and contractual completion.

## CONSTRUCTION PROGRESS SCHEDULE TIME IMPACT ANALYSIS

### If the CONTRACTOR requests an extension of the Contract Time or any Contract Milestone, the CONTRACTOR shall provide a CPS Time Impact Analysis (TIA) to support the request. At a minimum, the CPS Time Impact Analysis must contain the following:

#### A detailed network analysis based on the current approved “Baseline” CPS.

#### The Contract milestones affected and the number of additional days requested for each milestone extension.

#### A listing of all activities and logic added, deleted or changed which encompass the impact of the change.

#### A complete submittal of “before and after” CPS as detailed in this specification.

#### The CONTRACTOR’s entitlement for the request of an extension of the Contract Time and or Contract Milestone shall clearly demonstrate that impact to the CPS Critical Path has occurred resulting from the TIA.

#### The recommended guidelines that govern the Time Impact Analysis process can be found within AACE International Recommneded Practice no. 52R-06. “Time Impact Analysis – As Applied in Construction”, latest version.

# PART 3 – EXECUTION

## 3.01	CONSTRUCTION PROGRESS SCHEDULE SUBMISSION AND REPORTING REQUIREMENTS TABLE:

### The reports required by this section are to be prepared and submitted by the CONTRACTOR in accordance with Table 01 32 16-1 below.

Table 01 32 16-1: Table of Schedule Submittal Requirements

| S No. | DESCRIPTION | SUBMITTED AT PRE-CON | SUBMITTED MONTHLY | SUBMITTED AS SPECIFIED |
| --- | --- | --- | --- | --- |
| 1. | Identification Scheduling personnel. | v |  |  |
| 2. | Baseline Construction Progress Schedule | 5 days prior |  |  |
| 3. | Construction Progress Schedule Updates |  | v |  |
| 4. | Time Impact Analysis |  |  | v |
| 5. | Revised Construction Schedules/ Recovery Schedules |  |  | v |
| 6. | Schedule Narrative report | v | v |  |

.

END OF SECTION 01 32 16