SECTION 01 32 16

CONSTRUCTION PROGRESS SCHEDULE (use for larger, complex projects - consult with MSD Project Manager)

# PART 1 - GENERAL

## SECTION INCLUDES

### Scope.

### Software/Interface Requirements.

### Quality Assurance.

### Use of Float.

### Float Suppression.

### Non-Compliance.

## RELATED SECTIONS

### General Conditions are included in Section 00 72 00, including Paragraph 6.04.

### Contract Considerations are included in Section 01 26 00,  including Paragraph 1.03, Schedule of Values

### Submittals are included in Section 01 33 00.

### Project Meetings are included in Section 01 31 19.

### Substantial Completion as included in Section 01 77 19.

## SCOPE

### A clear and complete Construction Progress Schedule (CPS) is required for the Project. Most importantly, the CPS shall be a tool which the CONTRACTOR and his agents will use to manage their Work and scope of the Project. The schedule must provide a tool that all parties involved in the Project can use to understand the status of and intended Project plan throughout the execution of the Project.

### The CONTRACTOR is responsible for coordinating his own schedules (including Subcontractors) as well as construction activities of others directed by the CONTRACTOR. The CONTRACTOR shall maintain the overall project CPS, of which the other CONTRACTORs’ and subcontractors’ CPS will be a part.

### The CPS, including all variations thereof, shall be in accordance with the requirements of the Contract Documents, including Paragraph 6.04 of the General Conditions.  The CITY’s review or acceptance of any schedule shall not relieve the CONTRACTOR from responsibility for complying with the requirements of the Contract Documents, adhering to those sequences of Work indicated in or required by the Contract Documents, or from completing any Work omitted from the schedule, within the Contract Time.

### The Work under the Contract Documents shall be planned, scheduled, executed, and reported by the CONTRACTOR using a cost-loaded, Critical Path Method ("CPM") schedule utilizing a Work Breakdown Structure ("WBS").  The CONTRACTOR shall adhere to industry established technical standards for CPM scheduling using a computerized Precedence Diagram Method ("PDM").  The CONTRACTOR is required to provide baseline and progress status data as specified further herein.  The CITY can and may request the CONTRACTOR to provide additional details.

### All accounts in the Schedule of Values shall correspond to a WBS rollup in the CONTRACTOR’s CPS.  All activities tied to a Schedule of Values ("SOV") account number must be assigned a budget value. The budget totals in the schedule shall balance with the SOV totals.  The SOV shall be prepared and submitted in accordance with Contract Considerations, Section 01 26 00, Paragraph 1.03.

### The CITY may provide the CONTRACTOR with Interim and Contractual Milestones to be included in the CPS.  It is the CONTRACTOR’s responsibility to include these Milestones in the logical sequence of activities in the CPS.  If the CITY provides Interim and Contractual Milestones, these dates shall only be changed by an approved Change Order.

### Days are defined herein as calendar days.  A day is defined as twenty-four hours (24) hours, commencing at midnight upon a given date and ending at midnight on the following date.

### If the CONTRACTOR should propose to complete the Work earlier than any required milestone or completion date, the CITY shall not be liable to the CONTRACTOR for any costs or other damages should the CONTRACTOR be unable to complete the Work before such milestone or completion date.

## SOFTWARE/INTERFACE REQUIREMENTS

### The CONTRACTOR shall use modern CPM scheduling software to produce the Construction Progress Schedules including all Project schedules, and reports as specified. This software shall run on the Microsoft (MS) Windows operating system. It shall be commercially available for lease or purchase and capable of processing and plotting schedule data as specified in this Section.  All Schedules shall be submitted on the latest version of the Primavera P6 software or other approved software that is compatible with Primavera P6 software.

### Equivalent Software:

#### Reference is made to Primavera Project Manager Version P6 software as the approved format for schedule submittal in these Specifications. However, the CITY reserves the right to accept a schedule submittal using equivalent software that is compatible with the Primavera P6 software and approved by the CITY.

#### To be approved as an Equivalent or "Or Equal" software format the software must be “completely” compatible with the CITY’s Primavera Project Manager Version P6 database. Before software can be considered “completely” compatible it must be capable of producing schedule submittals in a format that can be imported into the CITY’s Primavera Project Manager Version P6 database without distortion of any coding or relationships contained in the submitted file.

#### The contractor shall only utilize equivalent or compatible software, which has received written approval from the CITY prior to their submittal of their proposal for the Contract Work.

## QUALITY ASSURANCE

### The CONTRACTOR shall employ a firm or individual to perform the work covered by this section that shall have substantive experience in using computer based scheduling programs on construction projects (the "Scheduling Consultant").  The CONTRACTOR shall submit the following as a minimum:

#### Identification, qualifications, and experience of the members of the CONTRACTOR’s scheduling staff or any consultant’s staff.  The designated Scheduling Consultant shall have at least five (5) years of experience in the computerized scheduling of public or industrial construction work.  The CONTRACTOR shall provide a resume for the designated individual(s) that details all qualifications, experience, and references for the CITY’s approval.

#### The CITY may reject any member of the CONTRACTOR’s scheduling staff or any of Contractor's Scheduling Consultant’s staff.  The CONTRACTOR shall promptly replace rejected personnel and resubmit the above required qualifications for acceptable personnel at no additional cost to the CITY.

## USE OF FLOAT

### Unless otherwise indicated herein, float and total float are synonymous. Total float is the period of time measured by the number of Days by which an activity can be delayed before it and its succeeding activities become part of the critical path. If a non-critical path activity is delayed beyond its float period, then that activity becomes part of the critical path and could impact the end date of the Work. Thus, delay of a non-critical path activity beyond its float period will cause delay to the project itself. Total float belongs to the Project and is not for the exclusive use of any party. Total float shall be available to the CITY and the CONTRACTOR, to accommodate changes in the Work, or to mitigate the effect of events that may delay performance or completion.  The CONTRACTOR will monitor and optimize the use of float for the benefit of the Project.

## FLOAT SUPPRESSION

### The CONTRACTOR shall not use any float suppression techniques, e.g., preferential sequencing (crew movements, equipment use, for reuse, etc.), extended durations, imposed dates, scheduling of non-critical work, artificial logic, and others, in preparation and maintenance of the schedule. Use of any type of schedule constraints must be identified in the CONTRACTOR’s submittal.

## NON-COMPLIANCE

### Pending an acceptable submission of the CPS, no partial payment will be made except in such amounts as may be approved by the CITY for materials received at the Project Site, plus any additional amounts that the CITY decides to release.

# PART 2 - PRODUCTS

## CONSTRUCTION PROGRESS SCHEDULES GENERAL CRITERIA

### The CONTRACTOR shall use a Work Breakdown Structure (WBS) (i.e., project, area, facility, activity codes, etc.) to identify the hierarchy of Work that must be accomplished to complete the project. The WBS is structured in levels of Work detail, beginning with the product itself, and then is separated into identifiable work elements for developing the activity I.D. and coding structures. The proposed WBS structure shall be presented and explained by the CONTRACTOR at the Pre-Construction meeting.

### The CPS shall include, but not limited to baselines, updated schedules, revised schedules, and recovery schedules.  All CPSs shall be prepared by the CONTRACTOR and reflect the CONTRACTOR’s plans for and status of the Work and shall comply with the requirements of the Contract Documents.  When Submitting Construction Project Schedules, the CONTRACTOR shall submit the schedule in PDF format and the designated Primavera Project Manager Version P6 software file format. CPSs and supporting documentation shall be provided at the intervals listed in Table 01 32 16-1: “Table of Schedule Submittal Requirements” or as requested by the CITY.

### The CPSs shall show the breakdown of Work into activities and respective relationships to the extent required to effectively manage the Work.  The CPSs shall show the division of the Work into activities and specify the progression from the Notice to Proceed (NTP) to the completion of the Work and shall be logically linked to include all milestones.  Each construction activity shown on the CPSs shall have a respective budget value, a portion of the Contract Sum.

### The CONTRACTOR shall allow for inclement weather in the CPSs. The weather allowance shall be detailed as a line item included in the Critical Path of the Project Work sequence. Allowances for weather shall be based on Paragraph 12.03(A)(2) of the General Conditions.  To the extent that CONTRACTOR has a valid claim for additional Time due to weather delays, Time extensions for weather will not be granted until disruptions to the Project progress exceed the scheduled allowance and the critical path is affected as shown in a Time Impact Analysis (see section 2.05 of this specification).

### The CONTRACTOR’s CPS shall include all procurement related activities that lead to the delivery of permanent materials to the site.  Procurement activities include, but are not be limited to, preparation of Submittals, review and acceptance of Submittals, materials fabrication, and materials delivery.

#### Schedule logic shall tie the procurement activities to the installation phase of the respective work scope.

#### The CONTRACTOR shall prioritize the Project material and equipment submittals.

#### In particular, the CONTRACTOR shall identify “Long Lead Time” equipment and material items and schedule their submittal appropriately.

### CONTRACTOR shall allow for Shutdown dates and necessary notification times in the CPS.  The Shutdown allowance shall be detailed as a line item included in the Critical Path of the Project Work Sequence.  The Shutdown dates are identified in paragraph 4.2.2 of the City-Contractor Agreement in Section 00 52 01.

## CONSTRUCTION PROGRESS SCHEDULE BASELINE SUBMISSION

### The CONTRACTOR shall prepare and submit a Baseline Construction Progress Schedule (CPS) for review prior to the Pre-Construction Meeting.  The Baseline CPS submission is required a minimum of five working days prior to the Pre-Construction Meeting.

### The CONTRACTOR’s Baseline CPS shall consist of a minimum of the following:

#### A pure logic Precedence Diagram Plot grouped by WBS, early start and early finish.  The plot must clearly and legibly show all activities and logical ties and shall display each activity’s identification number, description, original duration, remaining duration and total float value.  The plot shall clearly show the critical path. A Gantt chart plot shall also be acceptable.

#### The CPS must clearly show the sequence and interdependence of activities required for complete performance of the Work, beginning with the Contract Start Date (CSD) and concluding with the Contract Completion Date (CCD). The maximum duration of any physical work activity shall not exceed twenty (20) working days (or one reporting cycle) unless approved by the CITY.

#### In addition to the activities included in the Contract Documents, the network diagram and CPS will reflect the major interfaces between the Work required under the Contract Documents and the concurrent and succeeding work of the other contracts  deemed necessary by the CITY for Substantial Completion and turnover of the Project.

#### The original CPS Baseline submittal shall not have the use of negative lag on any activities along the critical path or near critical path.

#### Tabular activity reports will be required as directed by the CITY. The format will be discussed at or prior to the Pre-Construction Meeting. Activity data included in the tabular reports may include but is not limited to the following:

a.	Bid Item, SOV, WBS Level, Responsibility

b.	Activity ID., Early Start Date, Early Finish Date, Late Start, Late Finish, Free Float, Total Float

c.	Physical % Complete, Original Duration, Remaining Duration

d.	Predecessors, Successors, Lags

e.	Budget, Earned Value to Date, Earned Value this Period

f.	Cost Performance Index (CPI), Schedule Performance Index (SPI)

g.	“S” curves for resource usage

h.	“S” curves for project cash flow

- A schedule narrative as described in Paragraph 2.04 will be prepared and included with the submission of the original CPS.

- Addition reports or plots requested by the CITY.

B.	When the CONTRACTOR’s Baseline CPS is reviewed and approved by the CITY it becomes the CONTRACTOR's “Approved Baseline” CPS.  Any changes to the Approved Baseline CPS, other than status updates, require the approval of the CITY in accordance with the Modification provisions in the Contract Documents.

## CONSTRUCTION PROGRESS SCHEDULE MONTHLY UPDATES

### Updating the CONTRACTOR’S CPS with current status and proposed schedule changes is the responsibility of the CONTRACTOR. Contract Time (including all contracted milestones) shall not be changed without an approved Change Order or Work Directive Change issued by the CITY.

### The CONTRACTOR shall maintain and status the CPS. The CONTRACTOR shall prepare and submit a complete updated CPS for review and approval as requested by the CITY and as required by the Contract Documents. The CONTRACTOR shall update and status the CPS at a minimum on a monthly basis or as otherwise directed by the CITY.

### A Schedule Update of the CPS shall be submitted prior to the monthly progress meeting specified in Section 01 31 19 Project Meetings.

### Updating the schedule shall consist of the following:

#### Updating Activity Status:  At intervals requested by the CITY, the CONTRACTOR shall manually status the following:

##### Actual Start Dates.

##### Physical % Complete - Physical % Complete shall be reviewed at the monthly progress meeting or at intervals as requested by the CITY’s representative.

##### Remaining Duration - Remaining duration shall be the CONTRACTOR’S best estimate of the time required to complete activities that have started but not yet completed.

##### Actual Finish Dates.

##### Data Date - Will be set to correspond to the last day of the update period.

##### Based on the above listed items (a-e), the Contractor will recalculate the schedule.

#### Corrections to the Schedule:  Prior to subsequent submittals, the CONTRACTOR shall make those corrections to the CPS that were identified or requested at the last update by the CITY.

#### Revisions to the CPS:  Schedule Revisions are defined as any change to schedule activities or logic, other than 1) the updating of actual start and finish dates, 2) changing physical % complete of the Work, 3) changing remaining duration of activities, or 4) changing the dates for Substantial of Final Completion. No Revisions to the CPS shall be made to the Construction Progress Schedule unless approved by and or directed by the CITY.

#### Should Project Milestones or Project Completion indicate negative float, the CONTRACTOR may be required to submit a CPS Recovery Schedule per Paragraph 3.04 Construction Progress Schedule Recovery or a Construction Progress Schedule Impact Analysis per Paragraph 2.05, or both. The required submittal, by the CONTRACTOR, of a CPS Recovery Schedule or CPS Impact Analysis, shall be at the sole discretion of the CITY. The requested CPS Recovery Schedule or CPS Schedule impact analysis shall be provided to the CITY from CONTRACTOR no more than five (5) working days from date of request by the CITY.

#### After any CPS Revision is reviewed and approved by the CITY, the CONTRACTOR shall promptly incorporate the Schedule Revision into the Construction Progress Schedule.

##### Approved Schedule Revisions shall be made and incorporated into the CPS in accordance requirements of this specification and the Contract Documents.

##### No budget changes or time extensions shall be made to the CPS until a fully executed change order has been processed per the requirements of the Contract Documents.

## CONSTRUCTION PROGRESS SCHEDULE NARRATIVE

### A Schedule Narrative report shall accompany the initial Baseline submission of the CONTRACTOR’s CPS. The Schedule Narrative shall support and augment the CPM Construction Progress Schedule. The Schedule Narrative shall include, but is not limited to the following:

#### The Contract requirements and objectives.

#### A description of methods of operation.

#### A description of resources to be employed.

#### An explanation of the general sequence of the Work.

#### An explanation of the Project critical path.

#### A listing of any long lead equipment.

#### An explanation of physical constraints to completing the Work.

##### The basis of constraints and lags utilized in the Baseline CPS and subsequent Schedule Updates  must be documented in the CPS Narrative.

#### A description of any assumptions made in developing the CPS.

#### Time frames for the construction of major systems, achieving Substantial Completion, and completion of all Work.

### A CPS Narrative shall accompany each required update to the CONTRACTOR’s CPS and shall, at a minimum, address the following:

#### Milestones completed.

#### A descriptive summary of each Schedule Revision incorporated into the CPS since the last Schedule Update and it’s affect on the CPS.

#### Any change to the CPS critical path.

#### Any actual or anticipated problems with delivery of materials or equipment.

#### Any problems with submittal approval.

#### Any corrective action undertaken by the CONTRACTOR to address CPS problems.

#### Anything impacting critical path, milestones and contractual completion.

#### Schedule “slip” if indicated in the schedule submittal.

## CONSTRUCTION PROGRESS SCHEDULE TIME IMPACT ANALYSIS

### If the CONTRACTOR requests an extension of the Contract Time or any Contract Milestone, the CONTRACTOR shall provide a CPS Time Impact Analysis (TIA) to support the request. At a minimum, the CPS Time Impact Analysis must contain the following:

#### A detailed network analysis based on the current approved “Baseline” CPS.

#### The Contract milestones affected and the number of additional days requested for each milestone extension.

#### A listing of all activities and logic added, deleted or changed which encompass the impact of the change.

#### A complete submittal of “before and after” CPS as detailed in this specification.

#### The CONTRACTOR’s entitlement for the request of an extension of the Contract Time and or Contract Milestone shall clearly demonstrate that impact to the CPS Critical Path has occurred resulting from the TIA.

#### The recommended guidelines that govern the Time Impact Analysis process can be found within AACE International Recommneded Practice no. 52R-06. “Time Impact Analysis – As Applied in Construction”, latest version.

# PART 3 – EXECUTION

## SCHEDULE DEVELOPMENT

### CONTRACTOR’S BASELINE CONSTRUCTION PROGRESS SCHEDULE:

#### The CONTRACTOR shall submit the CONTRACTOR’S Baseline CPS via e-Builder®.

##### The electronic copies will be formatted in PDF file type on 11”x17” layout.

##### The CONTRACTOR will also submit the CPS in electronic Primavera file format of one of the following types: PRX, XER, and/or STX. Layout files shall also be included with the electronic Primavera file format.

#### All CPS reviews provided to the CITY will be processed in accordance with Section 01 33 00 Submittals.

#### If revisions are requested by the CITY, the CONTRACTOR shall make appropriate adjustments or revisions and shall re-submit the revised CONTRACTOR’S CPS for review and approval.

#### If the CONTRACTOR makes changes or revisions additional to those requested by the CITY, the CONTRACTOR shall provide a narrative for those revisions and illustrate the resulting change and/or impact to the CPS Project Critical Path.

#### The CITY’s review is for compliance with the Contract Documents.  The review shall not extend to the CONTRACTOR’S means, methods, or techniques, which shall remain the sole responsibility of the CONTRACTOR.

#### Once the CONTRACTOR’S CPS is accepted it becomes the “Baseline” CONTRACTOR’S CPS for the Work, and is the basis for:

##### Monitoring the CONTRACTOR’S progress against milestones and Contract Time.

##### Evaluation and reconciliation of extensions in Contract Time.

##### Review and acceptance of the CONTRACTOR'S Applications for Payment.

## UPDATE OF THE CONTRACTOR’S CONSTRUCTION PROGRESS SCHEDULE

### The cut-off date (Data Date) for the CPS Updates shall be determined prior to or at the Preconstruction Meeting.

### Construction Progress Schedule Update Submittals:

#### A current updated version of the CONTRACTOR’S CPS shall accompany (attached to) each Application for Payment.

#### Neither the updating of the CONTRACTOR’S CPS, nor the updating of any report submitted by the CONTRACTOR under this section shall have the effect of amending or  modifying, in any way, the Contract Time, Contract Completion Date, or Contract Milestone Dates.

#### CPS calculation settings shall be as listed below (note: the below criteria only applies if the CONTRACTOR utilizes Pimavera software).

##### Calculate start-to-start lag by using Early Start option.

##### Calculate Early Start using Contiguous activity duration option.

##### Calculate total float using most critical option.

##### Calculate critical activities and critical path shall be set to “Total Float” equal to or less that zero.

##### Use Retained Logic

## CONSTRCUTION PROGRESS SCHEDULE REVISIONS

### If requested by the CITY, the CONTRACTOR shall provide a separate subnetwork schedule within the CPS monthly update for each proposed revision showing the revised activities and illustrate their proposed incorporation into the CONTRACTOR’S CPS.

## CONSTRUCTION PROGRESS SCHEDULE RECOVERY

### In the event that an updated CPS indicates that the Project, or a Milestone requirement, “falls behind schedule or slips” and there is no change to support a time extension, CONTRACTOR shall prepare and submit a CPS Recovery Schedule for review within five (5) working days from the CITY’s request.  The CPS Recovery Schedule shall consist of proposed revisions to the CONTRACTOR’S CPS demonstrating how the CONTRACTOR intends to achieve all contractual milestones, including contract completion dates, within the allotted Contract Time. An accompanying CPS Narrative Report shall describe the cause/effect scenarios related to the “schedule slip”  and the actions planned by the CONTRACTOR to recover lost time.

### The CONTRACTOR shall promptly undertake appropriate action at no additional cost to the CITY to recover lost time.  Appropriate recovery actions may include, but not be limited to, assignment of additional labor and/or equipment, shift or overtime work, expediting of submittals or deliveries, overlapping of activities or sequencing changes to increase activity concurrence.

### Lack of Action:  In the sole discretion of the CITY, if the CONTRACTOR fails to take appropriate recovery action and or submit a CPS Recovery Schedule in a timely manner, the CITY may withhold payment to the CONTRACTOR until such time that the CITY deems that the CONTRACTOR has in fact taken adequate and appropriate action to recover the Project.

## CONSTRCUTION PROGRES SCHEDULE SUBMISSION AND REPORTING REQUIREMENTS TABLE:

### The reports required by this section are to be prepared and submitted by the CONTRACTOR in accordance with Table 01 32 16-1 of this section.

Table 01 32 16-1: Table of Schedule Submittal Requirements

| S No. | DESCRIPTION | SUBMITTED Prior to or AT PRE-CON | SUBMITTED MONTHLY or as Requested by the CITY | SUBMITTED AS SPECIFIED |
| --- | --- | --- | --- | --- |
| 1. | Identification of Scheduling Software and Scheduling personnel. | v |  |  |
| 2. | Baseline Construction Progress Schedule | 5 days prior |  |  |
| 3. | Construction Progress Schedule Updates |  | v |  |
| 4. | Revised Construction Progress Schedules/ CPS Recovery Schedules |  |  | v |
| 5. | CPS Time Impact Analysis |  |  | Per CITY |
| 6. | CPS Narrative report | v | v |  |
| 7. | Other reports when requested |  |  | Per CITY |

.

END OF SECTION 01 32 16