SECTION 01 75 00

COMMISSIONING REQUIREMENTS AND SEQUENCE

# GENERAL

## SECTION INCLUDES

### Scope.

### Submittals.

## RELATED SECTIONS

NOTE TO SPECIFIER:	Under item C below, a table of cross references to other specification sections where warranties are called for is recommended.  In addition, a disclaimer is required regarding warranty requirements not being all inclusive due to the fact that some requirements may be included elsewhere in the Contract Documents.

### Drawings and general provisions of the contract, including General Conditions, Special Provisions, and other Division 1 Specification Sections apply to this Section.

### Manufacturer Product Warranties are included in Section 01 78 36.

### Contractor’s General Condition Warranty and Guarantee are included in the General Conditions, Section 00 72 00, Article 6.19.

### Equipment Factory Acceptance Testing, Section 01 75 01.

### Equipment Startup and Checkout, Section 01 75 02.

### System Functional Testing, Section 01 75 03.

### Process Performance Testing, Section 01 75 04.

### Operational Testing, Section 01 75 05.

### 30-Day Commissioning Reliability Test, Section 01 75 06.

### Substantial Completion, Section 01 79 00

## SCOPE

### The CONTRACTOR shall follow procedures to assure that the correct equipment is installed, that the equipment is properly installed, that all supporting documentation is complete and accurate, and that all equipment, systems and processes operate as specified and submitted.

### The procedures to be followed are outlined in the following sections:

### Equipment Factory Acceptance Testing, Section 01 75 01.

### Equipment Startup and Checkout, Section 01 75 02.

### System Functional Testing, Section 01 75 03.

### Process Performance Testing, Section 01 75 04.

### Operational Testing, Section 01 75 05.

### 30-Day Commissioning Reliability Test, Section 01 75 06.

### The requirements and expectations for each of these sections are indicated in each respective technical section.

### The CONTRACTOR shall include adequate and itemized scheduling requirements for each of the Startup and Verification tasks in the overall Construction Progress Schedule.

### All Startup and Verification provisions in the Contract Documents shall be completed, and the sequence shall follow the exact order in which these are listed in the Specifications.  Each section contains an Execution section and Documentation section, which shall be completed and approved prior to the start of any subsequent Execution section or Documentation section.  As indicated in the subsequent sections, the CONTRACTOR shall actively coordinate and participate with the CITY to complete these tasks in an efficient and timely manner.

### Flow charts of the Commissioning Requirements and Sequence are included at the end of this section.

### A Master Commissioning Checklist is available from the City and is to be used in the commissioning process.

## SUBMITTALS

### Commissioning Requirements and Sequence.  The CONTRACTOR shall separately submit the sections of the overall Construction Progress Schedule which are applicable to Commissioning Requirements and Sequence.

1.05	FLOW CHARTS

End prior to Substantial Completion

END OF SECTION 01 75 00