SECTION 01 75 05

OPERATIONAL TESTING

NOTE TO SPECIFIER:  The Operational Testing specification section (01 75 05) is for testing a process (equipment or system) under specified operating conditions and must be performed using the process media for which the process was designed (i.e., the use of surrogate media is not permitted).  The testing is performed to verify that the equipment and systems are operating properly with a focus on meeting specified operational parameters. The testing should be done over the entire specified performance range (minimum through maximum).

# PART 1 - GENERAL

## SECTION INCLUDES

### Scope.

### Definitions.

### Submittals.

## RELATED SECTIONS

NOTE TO SPECIFIER:	Under item A below, a table of equipment to be started and checked is to be provided.  In addition, a disclaimer is required regarding startup and checkout activities not being all inclusive due to the fact that some requirements may be included elsewhere in the Contract Documents.

### Drawings and requirements of the contract as put forth in the various portions of the Project Manual, including General Conditions, any Special Provisions, and other Division 1 through Division XX Specification Sections and addenda apply to this Section.  A Partial list of specification sections where Operational Testing are indicated as being required is presented for convenience in the table appearing below but this summary is not guaranteed to be all inclusive of all references and related sections for Operational Testing that may appear elsewhere in the Contract Documents (Contractor’s attention to any addenda modifications is of particular importance).

| Title of Specification Section | Specification Reference Number | Comments |
| --- | --- | --- |

### Drawings and general provisions of the contract, including General Conditions, Special Provisions, and other Division 1 Specification Sections apply to this Section.

### Manufacturer Product Warranties are included in Section 0178 36.

### Contractor’s General Condition Warranty and Guarantee are included in the General Conditions, Section 00 72 00, Article 6.19.

### Commissioning Requirements and Sequence, Section 01 75 00.  (See Part 4 for the Operational Testing flow chart associated with this Section.)

### Equipment Factory Acceptance Testing, Section 01 75 01.

### Equipment Startup and Checkout, Section 01 75 02.

### System Functional Testing, Section 01 75 03.

### Process Performance Testing, Section 01 75 04.

### 30-Day Commissioning Reliability Test, Section 01 75 06.

## SCOPE

### Operational Testing shall be performed to verify proper powered operation of a process, under actual operating conditions, and using the process media for which the process was designed.

### Operational Testing shall be performed by the CONTRACTOR with MSD or MSD’s Consultant to verify proper operation, as described by the following items, as outlined in the technical specifications.  Refer to each appropriate technical specification section for the operational requirements or expectations.  Operational requirements may be specified for various media conditions and levels of operation, including equipment, system and process.

#### Specific operational parameters or expectations.

#### The Functional Description, complete.

#### The Sequence of Operation.

#### Alternative modes of operation.

#### Process functionality, using process or surrogate media as practical.

#### Process or system upsets and recovery.

### For each of the items listed, the CONTRACTOR shall plan, schedule, execute and document the Operational Testing of the applicable and related equipment, systems and processes.

### In accordance with Section 01 75 00, Commissioning Requirements and Sequence, Operational Testing shall be only initiated subsequent to the approved Successful Completion of Process Performance Testing, Section 01 75 04.

### Operational Testing shall be performed by the CONTRACTOR, and witnessed by the CITY.

### The CONTRACTOR shall utilize the services of the Testing Manager, defined and approved in the Performance Testing section.  The Testing Manager shall oversee and directly supervise all aspects pertaining to Operational Testing.

## DEFINITIONS

### Successful Completion.  All aspects of Operational Testing have been completed, and all requirements listed in the specifications and in the submittals have been proven to have been met, within the specified constraints.  Conformance to test plan requirement will be the commissioning checklist.

### Testing Manager.  The person appointed by the CONTRACTOR to plan, schedule, manage, coordinate, and supervise the CONTRACTOR’s Performance Testing and Operational Testing programs, including Submittals, Execution and Documentation.

### System.  Regarding Operational Testing, a system shall include all items of equipment, devices and appurtenances connected such that the operation or function of each complements, protects or controls the operation or function of the others.  The following are examples of systems used in wastewater facilities: pumping, flow measurement, programmable controller, level controls, compressor, centrifuge and boiler.

### Process.  Regarding Operational Testing, a process shall include a collection or series of systems or equipment, which act together upon a fluid media to cause a separation or change in properties, location or energy.  The following are examples of wastewater processes: grit removal, clarification, aeration, dewatering and incineration.

## SUBMITTALS

### Testing Manager.  The CONTRACTOR shall submit confirmation that the Testing Manager appointed under the requirements of Performance Testing, Section 01 75 04, shall be the same individual performing the Testing Manager tasks, outlined as follow.  A proposed change of Testing Manager shall be submitted for approval.  The Testing Manager confirmation shall be approved prior to the Testing Manager’s development of all subsequent submittals in the Operational Testing section.

### Operational Testing Plan.  A set of detailed Operational Testing plans shall be submitted for approval by the Contractor.  The Operational Testing may begin 2 weeks after approval by the City.  Each test plan shall be specific to the process to be tested.  Each test plan shall include detailed descriptions of the preparation, execution and documentation, as follows:

#### A detailed list of the equipment, systems and processes to which the Operational Testing procedures will apply.  This list shall include at least all applicable mechanical, electrical, instrument, controls, HVAC and process equipment and systems.

#### The CONTRACTOR shall submit for review of a crane load test proposal, for all cranes installed, for CITY approval prior to testing.

#### Copies of all Functional Descriptions, Alternative Modes of Operation, Sequence of Operations, and Outline of System Upsets and Recovery to be tested, simulated and verified by the Operational Testing.

#### Complete descriptions of the preparation procedures necessary to achieve the desired test conditions.

#### A detailed list of procedures by which the CONTRACTOR plans to adequately and completely perform each aspect of the Operational Testing.  The compiled list of testing procedure shall address all components of all descriptions - Functional Description, Mode of Operation, Sequence of Operations or System Upset and Recovery.

#### A list of test and support equipment and other resources required to complete the test plan.

#### A list of personnel, who will be used to perform Operational Testing.  This list shall indicate all subcontractors or representatives of manufacturers or vendors required to be present for testing.  At the CITY’s discretion, the qualifications of personnel shall be documented and provided upon request.

#### An outline of specific resources to be provided by the CITY, such as the isolation of systems or processes.

#### Verification of the validity or calibration of the test equipment or resources to be used.

#### A detailed outline of the specific results or observations, which will constitute successful completion of each Operational Testing plan.

#### Sample documentation to be used to record the procedures and results of each Operational Testing plan, including a sample of each form to be used.  Samples of the format and level of detail required for the documentation forms are available in Section 01 33 19

### Operational Testing Schedule.  A detailed Operational Testing Schedule shall be submitted for approval.  This submittal shall accompany the Operational Testing Plan submittal.  Requirements of the schedule are as follows:

#### 1.	The proposed date that Operational Testing is to begin, and the estimated completion date.

#### 2.	A sequence, and relative daily schedule, by which the Operational Testing will be executed.

#### 3.	The proposed Operational Test dates shall be indicated on and coordinated with the CONTRACTOR’s construction schedule specified in Section 01 32 16.

### Operational Testing Documentation and Results.  Upon completion of all aspects of Operational Testing, all documentation indicating compliance with the requirements shall be signed and dated by the Testing Manager for completeness and accuracy, and by the CITY as witness.  A copy of the signed results shall be submitted to the CITY for consideration of Successful Completion.

### For items requiring only Certified Operational Testing, documentation of this certification shall be submitted to the CITY for approval.

# PART 2 - PRODUCTS

# NOT USED

# PART 3 – EXECUTION:  OPERATIONAL TESTING

## 3.01       PREPARATION

### The Testing Manager shall inform and coordinate the activities of all individuals required for Operational Testing, including the CONTRACTOR, all subcontractors, vendors, suppliers, the CITY’s operations and maintenance personnel, and other resources needed to implement the requirements of this section.

### The Testing Manager shall assure that all preliminary and cursory installation reviews have been performed and mitigated, including inspections of connections, fittings, mountings, leaks, pressures, temperatures, vibrations, electrical measurements, rotations and alarms.  The testing areas shall be cleaned and free of installation equipment and debris.  All safeties, guards and interlocks shall be completed and placed for operation.  All temporary equipment and configurations, including bypasses and jumpers, shall no longer be required and shall be removed.

### All test equipment and analysis instruments to be used for Operational Testing shall be available.  At the CITY’s discretion, test equipment or analysis instruments may be subject to re-verification after completion of the Operational Testing.

## SCHEDULE

### The approved Operational Testing Schedule shall be followed.

### The schedule shall be updated and posted weekly, showing actual dates of testing, and the status of each test plan.  Operational Testing procedures and schedules shall be contiguous, only interrupted for necessary modifications, adjustments, repairs and field engineering, as required for successful completion.  If any interruption exceeds 4-hours, the Testing Manager shall provide at least 24 hours notice to the CITY and all resources, prior to continuation or restart of the test plan.

## OPERATIONAL TESTING

### Operational Testing shall proceed under the direction of the Testing Manager.  Only one process and one Operational Test plan shall be executed at a time.  All Operational Testing shall follow the approved plans and schedules.

### If any test plan is not completed successfully, necessary modifications, adjustments, repairs or field engineering shall be performed as required for successful completion.  Operational Testing shall continue or be repeated until successful completion is accomplished.

### At the discretion of the CITY, previously completed Operational Test plans shall be repeated if subsequent modifications may have altered the equipment, system or process, and to have logically affected previous test results or observations.

### Any proposed deviation from the approved plans or schedules shall require written authorization by the CITY.

## DOCUMENTATION

### As each procedure is completed, the results shall be documented, dated and signed by the Testing Manager.  The CITY will also sign and date the documentation as witness.

### The CONTRACTOR shall maintain a list of Operational Testing Deficiencies, which shall be updated and sent to the CITY at the end of each week.

### Upon completion of all Operational Testing, all completed and witnessed documents shall be compiled and formally submitted for approval.  Unless a waiver is granted in writing by the CITY, partial submittals of individual equipment, systems or processes shall not be submitted for review or considered for approval.

PART 4 – FLOW CHART

Refer to 01 75 00 Section 2 for the Operational Testing workflow.

END OF SECTION 01 75 05

THIS PAGE LEFT BLANK INTENTIONALLY